## Sheet1
Task | Prerequisite | Sequential/Parallel | Total Hours | Estimation in days/resource | Resource | Total Days | Start Date | End Date | Status
Prototype |  | Sequential | 18 | 3 | 1 | 3 | 2022-08-23 | 2022-08-26 | Done
UML(Activity Diagram, Use Case Diagram, Component Diagram) | Prototype | Parallel | 42 | 10 | 1 | 10 | 2022-08-28 | 2022-09-09 | In Progress
BPD | Prototype | Parallel | 60 | 7 | 1 | 7 | 2022-08-30 | 2022-09-08 | In Progress
FSD | UML | Sequential | 60 | 10 | 1 | 10 | 2022-09-09 | 2022-09-23 | Incomplete
UX | FSD | Sequential | 60 | 10 | 1 | 10 | 2022-09-23 | 2022-10-07 | Incomplete
Mock API request/response | UX | Sequential | 960 | 160 | 1 | 160 | 2022-10-07 | 2023-05-19 | Incomplete
Mobile App | Mock API request/response | Parallel | 480 | 80 | 1 | 80 | 2023-05-19 | 2023-09-08 | Incomplete
Web FO | Mock API request/response | Parallel | 480 | 80 | 1 | 80 | 2023-05-19 | 2023-09-08 | Incomplete
Web BO | Mock API request/response | Parallel | 240 | 40 | 1 | 40 | 2023-05-19 | 2023-07-14 | Incomplete
Middleware and RDBMS |  | Parallel | 1080 | 180 | 1 | 180 | 2023-05-19 | 2024-01-26 | Incomplete
Testing (Unit and e2e) |  | Sequential | 720 | 120 | 1 | 120 | 2024-01-26 | 2024-07-12 | Incomplete
Total |  |  | 4200 |  |  | 700 |  |  | Incomplete
Project Start Date | 2022-08-23
Project Name | Digital Banking
Formulas:
End Date = WORKDAY([Start Date],[Total Days])
Start Date = [End Date, row above]